## Sheet1
Planning of Concern and Development Plan
App for contact between helpers and employers |  |  | Activity | Progress |  | Status of Budget(k)
| Original work | Full Design | Reviewing of Details and Making Sketch | All Done | 25 days | 3
www.figma.com design work
|  | Backend RestApi Development using Django | documenter.getpostman.com/view/5691075/2s7Z7YKaTj
|  | Front end React Design | Module development with all component
Figma design converting to figma
|  | Integrating Api | Confirming for Restful Api With Response
Integration on react.js with django api
|  | Additional Features | Feedback checking & fixing |  | 5 Days | 0.5
Location feature(with google map)
Listing pages with other idea
More Language Part
| Activity |  |  | Days Required | Total Days | Budgets(k)
| Re-planning & Implementation | Planning | AutoTranslation | 1 | 1 | 0.5
|  |  | HelperPlace app full testing | 1 | 2
|  |  | Location and sharing feature research from other app | 1 | 3
|  |  | Feedback | 1 | 4
|  |  | Prepare to start designing | 1 | 5
|  | Design | AutoTranslation Admin | 0.5 | 5.5
|  |  | AutoTranslation User Case | 0.5 | 6
|  |  | Location&sharing and new things for major design customization from HelperPlace | 1 | 7
|  | Implementation | AutoTranslation System Development | 3 | 10 | 1
|  |  | All backend work for new design | 1 | 11
|  |  | All change for front end like design | 1 | 12
1.5
[5 empty] | 12 Days | Total: 5 (k)